## Backlog
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | story points
5 | personalisaton | website visitor | be able to reset my password | I can still access my account even if I forget my password |  |  | 2 | 20 | As a / an website visitor I want to be able to reset my password so that I can still access my account even if I forget my password
12 | personalisaton | website visitor | be able to recover my username | I can access my account if I have forgotten my username |  |  | 2 | 20 | As a / an website visitor I want to be able to recover my username so that I can access my account if I have forgotten my username
6 | content | authenticated website visitor | see a customised homepage | I am more enagaged with the website |  |  | 1 | 50 | As a / an authenticated website visitor I want to see a customised homepage so that I am more enagaged with the website

## Done
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | closed in sprint | story points
1 | content | website visitor | view a home page | I can see the most important content at a glance and quickly understand the site navigation |  |  | 1 | 1 | 20 | As a / an website visitor I want to view a home page so that I can see the most important content at a glance and quickly understand the site navigation
2 | personalisation | website visitor | be able to log in to the site | I can see tailored content and manage my relationship with the company |  |  | 1 | 1 | 30 | As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company
3 | personalisation | website visitor | be able to register for an account | I can login and gain all the benefits of being an authenticated user |  |  | 1 | 2 | 80 | As a / an website visitor I want to be able to register for an account so that I can login and gain all the benefits of being an authenticated user
3 | personalisation | authenticated website visitor | be able to manage my profile details | I can update incorrect or changed details and view current records |  |  | 3 | 3 | 80 | As a / an authenticated website visitor I want to be able to manage my profile details so that I can update incorrect or changed details and view current records
4 | personalisation | authenticated website visitor | be able to log out of the website | my private information is kept secure when accessing the site on a shared computer |  |  | 1 | 3 | 10 | As a / an authenticated website visitor I want to be able to log out of the website so that my private information is kept secure when accessing the site on a shared computer

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
0 | 117 | 0 | 0 | 0% | 0 | 117
1 | 104 | 13 | 0 | 11% | 0 | 104
2 | 0 | 117 | 0 | 100% | 0 | 0
3
4
5
6
7
8
9
10
ID | Theme | as a/an | I want to… | so that… | added in sprint | Story points
| Content | User | Contact the developers | I can view team Info and logo | 2 | 1
| Content | Admin | Move shapes being rendered | I can edit shape properties | 2 | 10
| Content | Admin | Add or remove shapes and texts being renderd | I can edit shapes present on the canvas | 2 | 8
| Personalisation | User | Have my rendered shapes persist between uses | I do not have to recreate them each time | 2 | 40
| Personalisation | User | Be able to login to the application | I can use the actual program | 1 | 10
| Content | User | Have a toolbar with different buttons | I can help the user understand what to do | 1 | 3
| Personalisation | User | Be able to logout of the application | I can choose to login under a different account | 2 | 5
| Content | User | Have shapes from a .txt file render to the canvas | I can use them in the program | 2 | 20
| Personalisation | Admin | Be able to choose shape properties when adding | I can choose all shape properties on creation | 2 | 20

## Lists
0
5
10
20
30
50
80
130
200
400
1000